## Sheet1
# Epic | # User Story | User Story | priority | Planned Sprint | Assigned to | Duration(Hr) | Status
1 | 1 | As a user who orders food, I want to create account so that I can order a meal. | 1 | 1 | Mohamed | 8 | Done
1 | 2 | As an Administrator, I want to create account so that I can help both clients and deliveryman. | 1 | 1 | Omar | 8 | Done
1 | 3 | As a deliveryman, I want to create account so that I can communicate with an administrator in case I need help. | 1 | 1 | Ali | 6 | Done
1 | 4 | As a restaurant man, I want to create account so that I know what orders I need to prepare. | 1 | 1 | Mohamed | 7 | Done
2 | 1 | As a user who orders food, I want to view restaurants so that I can check the nearby places where I can order a meal. | 2 | 2 | Essam | 3 | Work in Progress
2 | 2 | As an Administrator, I want to view restaurants so that I can check If there is a problem in one of them. | 2 | 2 | Mahmoud | 9 | Work in Progress
2 | 3 | As a deliveryman, I want to view restaurants so that I know the addresses so I can get the food for clients. | 3 | 3 | Karim | 10 | Work in Progress
2 | 4 | As a restaurant man, I want to view restaurants so that I know the other nearby restaurants that cook the same food and may compete with them. | 4 | 3 | Omar | 4 | Open
3 | 1 | As a user who orders food, I want to search restaurants so that I know which one cook the type of food I want. | 5 | 3 | Ali | 7 | Open
3 | 2 | As an Administrator, I want to search restaurants so that I can further help users in searching process. | 5 | 4 | Ali | 9 | Open
4 | 1 | As a user who orders food, I want to view menu for a restaurant so that I know whats this restaurant offers. | 5 | 4 | Omar | 5 | Open
4 | 2 | As an Administrator, I want to view menu for restaurants so that I may help clients or restaurants if there is a problem in showing menu. | 7 | 4 | Mohamed | 2 | Open
4 | 3 | As a restaurant man, I want to view menu so that I can update the meals or their prices. | 7 | 5 | Mahmoud | 6 | Open
5 | 1 | As a user who orders food, I want to be able to add to cart so that I can complete my purchase. | 6 | 5 | Mahmoud | 4 | Open
6 | 1 | As a user who orders food, I want to be able to purchase so that I can get the meal I want. | 8 | 5 | Ali | 3 | Open
6 | 2 | As an Administrator, I want to be able to purchase so that I help the client if he/she has a problem in purchasing. | 9 | 6 | Essam | 6 | Open
7 | 1 | As a restaurant man, I want to view orders so that I can get them prepared. | 10 | 6 | Omar | 3 | Open
8 | 1 | As a restaurant man, I want to mark orders an delivered to ensure client satisfaction if he/she gets the meal at time. | 10 | 7 | Essam | 2 | Open